## FP
Complexity
Function Type | Low | Average | High
Internal Logic Files | 7 | 10 | 15
External Logic Files | 5 | 7 | 10
External Inputs | 3 | 4 | 6
External Outpurs | 4 | 5 | 7
External Inquiries | 3 | 4 | 6
|  |  |  | ILF | Complexity | FPs
|  |  |  | Login data | Low | 7
|  |  |  | User | Low | 7
|  |  |  | Car | Low | 7
|  |  |  | Ride | Low | 7
|  |  |  | PGS | Low | 7
|  |  |  | Safe Area | Low | 7
|  |  |  | Payment Details | Low | 7
|  |  |  | Total |  | 49
|  |  |  | ELF | Complexity | FPs
|  |  |  | Maps Api Response | Low | 5
|  |  |  | Payment Api Response | Low | 5
|  |  |  | Driving License Verification Response | Low | 5
|  |  |  | Total |  | 15
|  |  |  | EI | Complexity | FPs
|  |  |  | Registration | Average | 3
|  |  |  | Login/Logout | Low | 6
|  |  |  | Update User info | Average | 4
|  |  |  | Search Car | High | 6
|  |  |  | Reserve Car | Average | 4
|  |  |  | Cancel Reservation | Average | 4
|  |  |  | Open Car | Average | 4
|  |  |  | Unlock Car | Low | 3
|  |  |  | End Ride | Low | 3
|  |  |  | Report Issue | Average | 4
|  |  |  | Total |  | 41