## FP
Complexity
Function Type | Low | Average | High
Internal Logic Files | 7 | 10 | 15
External Logic Files | 5 | 7 | 10
External Inputs | 3 | 4 | 6
External Outputs | 4 | 5 | 7
External Inquiries | 3 | 4 | 6
|  |  |  | ILF | Complexity | FPs
|  |  |  | Login data | Low | 7
|  |  |  | User | Low | 7
|  |  |  | Car | Low | 7
|  |  |  | Ride | Low | 7
|  |  |  | PGS | Low | 7
|  |  |  | Safe Area | Low | 7
|  |  |  | Payment Details | Low | 7
|  |  |  | Total |  | 49
|  |  |  | ELF | Complexity | FPs
|  |  |  | Maps Api Response | Low | 5
|  |  |  | Payment Api Response | Low | 5
|  |  |  | Driving License Verification Response | Low | 5
|  |  |  | Total |  | 15
|  |  |  | EI | Complexity | FPs
|  |  |  | Registration | Average | 3
|  |  |  | Login/Logout | Low | 2x3
|  |  |  | Update User info | Average | 4
|  |  |  | Reserve Car | Average | 4
|  |  |  | Cancel Reservation | Average | 4
|  |  |  | Open Car | Average | 4
|  |  |  | Unlock Car | Low | 3
|  |  |  | End Ride | Low | 3
|  |  |  | Report Issue | Average | 4
|  |  |  | Total |  | 35
|  |  |  | EQ | Complexity | FPs
|  |  |  | Search Cars with position/address | Average | 4x2
|  |  |  | Search PGS with position/address | Average | 4x2
|  |  |  | Get Rides History | Low | 3
|  |  |  | Get Car Info | Low | 3
|  |  |  | Total |  | 22
|  |  |  | EO | Complexity | FPs
|  |  |  | Car Opened/Closed | Low | 2x4
|  |  |  | Car Locked/Unlocked | Low | 2x4
|  |  |  | Eco Mode notification | High | 7
|  |  |  | Total |  | 23
[7 empty] | Function Type | FPs
[7 empty] | Internal Logic Files | 49
[7 empty] | External Logic Files | 15
[7 empty] | External Inputs | 35
[7 empty] | External Outputs | 23
[7 empty] | External Inquiries | 22
[7 empty] | Total | 144

## COCOMO II
Scale factor | Rate Level
| Very Low | Low | Nominal | High | Very High | Extra High
PREC | 6.2 | 4.96 | 3.72 | 2.48 | 1.24 | 0
FLEX | 5.07 | 4.05 | 3.04 | 2.03 | 1.01 | 0
RESL | 7.07 | 5.65 | 4.24 | 2.83 | 1.41 | 0
TEAM | 5.48 | 4.38 | 3.29 | 2.19 | 1.1 | 0
PMAT | 7.8 | 6.24 | 4.68 | 3.12 | 1.56 | 0
[7 empty] | Scale Factor | Rate Level | Value
[7 empty] | PREC | Nominal | 3.72
[7 empty] | FLEX | Nominal | 3.04
[7 empty] | RESL | High | 2.83
[7 empty] | TEAM | High | 2.19
[7 empty] | PMAT | High | 3.12
[7 empty] | Total |  | 14.9
[10 empty] | Cost Driver | Level | Value
[10 empty] | RELY | Nominal | 1
[10 empty] | DATA | Very High | 1.28
[10 empty] | CPLX | Nominal | 1
[10 empty] | RUSE | Nominal | 1
[10 empty] | DOCU | Nominal | 1
[10 empty] | TIME | High | 1.11
[10 empty] | STOR | Nominal | 1
[10 empty] | PVOL | Low | 0.87
[10 empty] | ACAP | Nominal | 1
[10 empty] | PCAP | Very High | 0.76
[10 empty] | PCON | Very High | 0.81
[10 empty] | APEX | Low | 1.1
[10 empty] | PLEX | Nominal | 1
[10 empty] | LTEX | Nominal | 1
[10 empty] | TOOL | Very High | 0.78
[10 empty] | SITE | High | 0.93
[10 empty] | SCED | Nominal | 1
[10 empty] | Result |  | 0.60719